INTERNATIONAL KAVALA CONFERENCE, 9-10 November, 2006

ADVERTISING THE CITY – SUCCESSFUL EXAMPLES OF MARKETING CITIES IN EUROPE IN THE CONTEXT OF THE EUROPEAN COMPETITION OF CITIES

The City Marketing Pilot Plan of Nea Ionia, Magnesia, Greece: An Exercise in Branding

Alex Deffner

Assistant Professor of Urban and Leisure Planning

Director of the Laboratory of Tourism Planning, Research and Policy

Theodore Metaxas

# Adjunct Lecturer

Department of Planning and Regional Development

School of Engineering, University of Thessaly, Volos 383 34, Greece

# Abstract

The main aim of this paper is to present the various dimensions of the City Marketing Pilot Plan (CMPP) for Nea Ionia. This text focuses on the provision of a marketing plan guide, in order that the multidimensional image of Nea Ionia is effectively promoted. Ιt includes the processes of Place/ Distribution and Promotion, and the larger part focuses in two equally significant key issues. The first one is the analysis of the Critical Path Model (CPM) aiming at the provision of a strategic guideline to the planners and decision makers of Nea Ionia in order to implement the CMPP. The overall concept is to provide to Nea Ionia an element that in the forthcoming years will help in a strategic way the effective promotion and support of its multidimensional image. After analysing the economic profile of the area, the advantages and the current situation of the cultural sector, it evaluates which factors constitute the competitive advantage in culture, since culture is one of the main promotional axes of Nea Ionia. The second key issue is the analysis of the proposed marketing model of ‘8ps’ by Morrison. The text focuses on the creation and implementation of ‘packaging’ by taking account of the multidimensional character of Nea Ionia’s final provided good.

The CMPP is based on the Strategic Planning process, always starting from the identification of the city’s vision (focusing on its branding) and the primary urban development objectives that have to be satisfied.  Thus, the CMPP has a strategic character, based on its structure in connection to the identification of the most appropriate promotion methodology that provides the opportunity to the city to examine and evaluate some first results of the implementation of place marketing actions. A very important factor is that the CMPP has to take place in a particular temporal horizon (410 ‘working’ days), and during this period city’s actors, marketers and decision makers, have to collect and evaluate valuable information that is related with the development, or the change, of the CMPP structure either as a whole, or its parts.

The data for this paper are provided by the INTERREG IIIc CultMark project (Cultural Heritage, Local Identity and Place Marketing for Sustainable Development) that has been in operation in five European places since 2004: Nea Ionia/ Magnesia/ Greece (lead partner), Chester/ UK, Kainuu/ Finland, Rostock-TLM/ Germany and Pafos/ Cyprus.

Key words: city marketing, city branding, Critical Path Model, marketing model of ‘8ps’, strategic planning, CultMark project, Nea Ionia/Magnesia/Greece

# Introduction- City Branding

The role of city marketing has been increasingly important in Europe mainly aiming at three general target markets: residents, tourists, and businesses/ investors. Today it has become a necessity with regard to a plurality of processes e.g. global competition of cities, tourist attraction, urban management, city branding and urban governance. City marketing has faced many criticisms, the main one being that it substitutes for urban planning. However, according to Patteeuw and Urban Affairs, city branding is the planned image or brand of a city and it constitutes a challenge for urban planners (as well as architects) in the effort of cities to distinguish themselves aiming to respond to the increasing pressure of competition in the context of a globalised culture (2002).

As far as tourism is concerned, many destinations, irrespective of their spatial level (countries, regions, cities) or size (big, medium, small), are adopting branding strategies similar to those of the companies with brand names in an effort to differentiate themselves and to, not only emotionally, connect with potential tourists (Morgan et al., 2002/2004).

The main aim of this paper is to present the various dimensions of the City Marketing Pilot Plan (CMPP) for Nea Ionia, Magnesia, Greece. This text focuses on the provision of a marketing plan guide, in order that the multidimensional image of Nea Ionia is effectively promoted. Ιt includes the processes of Place/ Distribution and Promotion, and the larger part focuses in two equally significant key issues. The first one is the analysis of the Critical Path Model (CPM) aiming at the provision of a strategic guideline to the planners and decision makers of Nea Ionia in order to implement the CMPP. The overall concept is to provide to Nea Ionia an element that in the forthcoming years will help in a strategic way the effective promotion and support of its multidimensional image. After analysing the economic profile of the area, the advantages and the current situation of the cultural sector, it evaluates which factors constitute the competitive advantage in culture, since culture is one of the main promotional axes of Nea Ionia. The second key issue is the analysis of the proposed marketing model of ‘8ps’ by Morrison. The text focuses on the creation and implementation of ‘packaging’ by taking account of the multidimensional character of Nea Ionia’s final provided good.

The data for this paper are provided by the INTERREG IIIc CultMark project (Cultural Heritage, Local Identity and Place Marketing for Sustainable Development) that has been in operation in five European places since 2004: Nea Ionia/ Magnesia/ Greece (lead partner), Chester/ UK, Kainuu/ Finland, Rostock-TLM/ Germany and Pafos/ Cyprus. CultMark is applying a place marketing strategy with a cultural approach and its main aim is  to create a final successful image for each city/ region partner, as well as the study area as whole. We would like to express our thanks to the JTS INTERREG IIIC East and to the partners for the use of the delivered material.

# 1. The Definition of City Marketing as a Strategic Process

Place/city marketing constitutes one of the most interesting areas of research the last twenty years, since many cities, especially in Europe, use promotion policies in order to support their images and become competitive among other cities (Ashworth and Voogd, 1990; Kearns and Philo, 1993; Gold and Ward, 1994; Kotler et al, 1993; 1999; Duffy, 1995; Ward, 1998; Avraham 2000, 2004; Urban, 2002). Apart of the Anglosaxon experience there is also a strong German experience (Zerres, 2000; Tsegenidi, 2001; Konken, 2004). With reference to European regions and cities, Kotler et al. (1999) point out that the economic dynamism of a region/city also reflects on the development dynamics of that place, attributing an attractive or unattractive character to it. Regions/cities are characterised by their necessity to present, in their external environment, a positive image as far as their economic development is concerned, and for this reason they adopt promotional programmes and actions, which they subsequently implement (Hall, 1998/2001). In case of place marketing this product (Goodwin, 1993), or ‘good’ (Metaxas, 2003), is a place or a city or an island, especially when we talk about tourism destinations (Buhalis, 2000; Chaudhary, 2000) or tourism products (Meler and Ruzic, 1999; Morrison, 1989/2001), or destination products (Oppermann, 1996; Choi et al, 1999; Murphy et al, 2000; Morgan et al., 2002/ 2004).

Place/ city marketing concerns the adaptation of the traditional model of Marketing’s 4ps (product, price, place, promotion) and its performance in the procedure of place/city marketing. According to Short and Kim (1998), the realisation of place/ city marketing as a procedure is based, first of all, on the realisation of marketing procedure as a science and practice.  Marketing evolved largely among commercial enterprises in the inter-war period, as a means of selling physical products to paying customers for short-term financial profits (Ashworth and Voogd, 1994). Ashworth and Voogd (1990: 27) define place/ city marketing as:

a process whereby local activities are related as closely as possible to the demands of targeted customers. The intention is to maximize the efficient social and economic functioning of the area concerned, in accordance with whatever wider goals have been established. This definition significantly shifts the secondary definitions of product, customers and goals compared to conventional marketing.

Kotler et al (1999) support that:

place marketing refers to a place planning procedure concerning the satisfaction of the needs of target-markets. It could be successful when it satisfies two main parameters: a) the enterprises’ and the residents’ satisfaction from the purchase of goods and services that the place provides, b) the satisfaction of the expectations of potential target -markets (enterprises and visitors), as long as the goods and the services that the place provides to them are those that they wish to get.

The most significant issue is that the vision of the city and the development objectives and strategies, depend on the local distinctive characteristics and the particularities of each city and the strategic City Marketing Final Plan (CMFP) in order to become effective should based on these characteristics.

# 2. City Marketing in the Field of Culture and Tourism

The international experience indicates a focus on tourism and culture and shows an extensive variety of initiatives that concern urban regeneration, by using particular strategies and tactics (i.e. the cases of Sheffield – Bramwell 1998, Bradford – Hope and Klemm 2001, Pamplona and Holstebro in Spain – Kotler et al., 1999, York – Snaith and Haley 1999). All these cases focus on tourism development and use as tools some particular actions in order to achieve their main goals. These tools are: a) identification of the city’s environment strengths and weaknesses, b) identification and evaluation of cities’ particularities and distinctive characteristics, c) use and implementation of market research analysis, d) development of promotional policies, and e) development of partnership between city’s actors.

The existence of a sustainable and effective tourism and cultural economy is based on the capacity and knowledge of the places’ internal actors to create particular plans of action, by evaluating which fields of implementation of tourism and cultural policies could constitute a competitive advantage at a given time (Deffner and Metaxas, 2003). The contribution of tourism and culture must be related to the marketing of heritage (Misiura, 2005) the conformance and the implementation of urban policy actions, the focus on the satisfaction of the needs and demands of the potential target markets, the enforcement and promotion of the cultural identity and image of the place, the contribution of citizenship to achieving a better quality of life, and to the construction of a place competitive advantage.

# 3. The CultMark Project - its common and branding elements

CultMark (Cultural Heritage, Local Identity and Place Marketing for Sustainable Development) is an INTERREG IIIC project. CultMark is applying a place marketing strategy with a cultural approach. This means that it emphasizes the cultural dimension of marketing, as well as the promotion of the cultural resources of each place both in connection with the planning of demonstration actions.

The main aim of CultMark is to create a final successful image for each city/ region partner, as well as the study area as whole. The main objective is the development and implementation of innovative place marketing strategies, based on the elements of local identity and the cultural assets of the partner areas, in order to contribute to their sustainable economic and social development. Its secondary objectives include: the promotion of heritage as a significant factor in local and cultural development, the promotion and improvement of the investment climate of each area, the global promotion and support of the image of each area, the connection between place marketing and spatial development as an innovative approach to planning, the promotion and support of the representation of common developmental interests, the promotion and support of local knowledge and skills, the development of common and individual demonstration actions taking into account the particularities of each area, the support of the provision and diffusion of knowledge and know-how to actors, encouraging the development of entrepreneurial skills.

There exist various common elements in the demonstration actions: industrial heritage (Nea Ionia and Rostock), maritime heritage (Chester and Rostock), sport and event tourism (Nea Ionia as host of the 2004 Olympics football men and women preliminaries, Rostock Hansesail 2005 and as bidder, albeit unsuccessful, for the 2012 Olympics), festival tourism (Nea Ionia Blues and Rock, and Paphos Aphrodite festival), food tourism based on local cuisine (Nea Ionia and Kainuu), info kiosks (Nea Ionia for the 2004 Olympics, Paphos at the old harbour, and elsewhere), museums (Silk museum in Nea Ionia, Boat Museum in Ellsemere Port and Neston Borough Council in Chester). Perhaps the most 'unknown' action is the promotion of food tourism, which is characterized by such issues as: taste, protected names, events, festivals, food trail.

There also exist various unique elements that can function as 'branding devices': Olympic City image and legacy as well as Asia Minor traditions (Nea Ionia), most northern castle in the world and cross-cultural promotion (Russian, Swedish. Finnish) [Kajaani], promotion of leisure canals (Chester), signing of St Pauls's trails (Paphos).

# 4. The Production of the City Marketing Pilot Plan (CMPP) for Nea Ionia

City marketing needs a plan like urban planning needs a plan. The CMPP is based on the City Marketing Pre-Plan (CMP-P) and aims to establish the main axes for the preparation and the development of the City Marketing Final Plan (CMFP). Taking into consideration the CMP-P,, as well as the available data and all the reports that have been produced up till now in the context of the CultMark project, the CMPP aims to become a guideline for the effective implementation of the CMFP. The CMPP has a strategic character. It constitutes a significant means of CMFP implementation, in order for the image of each city to be effectively promoted and supported to the potential target markets. All plans are based on the strategic planning process, always starting from the identification of each city’s vision and the primary urban development objectives that have to be satisfied (CultMark, 2005b).

This paper uses material from the following reports that have already been delivered: a) ‘The Mini Investment Guide’ (it briefly provides concrete information for the economic and investment profile of the partner areas) [June, 2004], b) ‘The Strategies, Tactics and Alternative Scenarios Report’ (it deals with the application of specific strategies, tactics, and alternative scenarios of the promotion and support of the image of each area both in its external and internal environment) [June, 2004], c) ‘The Final Provided Good Report’ (it presents the final provided good for each area, based on the available research data and the local distinctive characteristics) [December, 2004], and d) ‘The Promotional and Distributional “Maps” Report’ (it presents the ways/ means of distribution and promotion of the image of each area both in its external and internal environment) [December, 2004], e) Cultural Data Report (it concerns the analysis of the internal environment of the cultural sector and the identification of its role in economic development) [June, 2005], f) City Marketing Pilot Plan for Nea Ionia [December, 2005] .

The structure of the CMPP is presented in Tables 1 and 2

Table 1: The structure of the City Marketing Pilot Plan

(use of primary data)

| Steps | Method | Purpose | Sources |
| --- | --- | --- | --- |
| The identification of the vision | ## Questionnaire 3 Interviews and survey-questionnaire analysis (open-ended questions and Likert scale 1-5) to ‘key’ local actors and decision makers in each place (sample: 20-30 individuals per place) [period: January to March, 2005] | Identify the factors that constitute advantages of the cultural sector Identify the vision and the image of each place | Cultural Data Report (June 2005) |
| The identification of the image as a final provided good | ## Questionnaire 2a ## A survey-questionnaire analysis (open-ended questions and Likert scale 1-5), to domestic visitors (70%) and foreign tourists (30%) (sample: 50-100 individuals per place) [period: June to September, 2004] ## Questionnaire 2b A survey-questionnaire analysis (open-ended questions and Likert scale 1-5), to ‘key’ local actors and decision makers in each place (sample: 20-30 individuals per place) [period: June to September, 2004] | Identify and evaluate visiting criteria to each place Identify and evaluate the degree of place capacity to satisfy the demands of the target markets | Final Provided Good Report (December, 2004) |
| The identification of the potential target markets | ## Questionnaire 2a and 2b | Propose the appropriate target markets for each place | Promotional and Distributional Maps Report (December, 2004) |
| The selection of the appropriate strategies | ## Questionnaire 2a, 2b and 3 | Identify tourism services provided by each place Identify promotional policies that are implemented by the local actors | Strategies, tactics and alternative scenarios report (June, 2004) |

Table 2: The structure of the City Marketing Pilot Plan

(Proposed methods and actions)

| Steps | Purpose | Sources |
| --- | --- | --- |
| Connection of the implementation of the selected strategies with the vision and the development objectives | To provide an important link between the selected strategies and the vision and the development objectives of each place, to the local decision makers | City Marketing Pilot Plan Report for Nea Ionia (December, 2005) |
| The implementation of Critical Path Analysis method | To provide a technical tool, based on project planning, by putting the whole CMPP, into a specific time horizon, identifying the primary and secondary actions per phase. | City Marketing Pilot Plan Report for Nea Ionia (December, 2005) |
| The implementation of ‘8ps’ model by Morrison | To present and propose a marketing mix model, that fixed to the effective promotion and support of the image of the places as final provided goods | City Marketing Pilot Plan Report for Nea Ionia (December, 2005) |
| The development of Communication process | Places decision makers and planners have the opportunity to audit the weaknesses of each step and each tactic in order to re-design or to re-construct the main strategies by using other alternative ones. | City Marketing Pilot Plan Report for Nea Ionia (December, 2005) |

# 5. The Case of Nea Ionia, Magnesia, Greece

## 5.1 Profile

The Prefecture of Magnesia, having a central geographical position in Greece and being almost equidistant from the two major urban centres of Athens and Thessaloniki, constitutes a very important junction. By having one of the most significance harbours of Greece (Volos) it has a developed system of sea transports and a high level of communication infrastructures in the sectors of transports and energy.

The urban agglomeration includes the municipalities of Volos, Nea Ionia and other smaller areas, and it has a population of about 130,000. Volos and the wider area have been developed as manufacturing and industrial centres, especially in the last three decades. The economy of the city is based on the industrial and the service sector.

An important advantage in the attempt for Nea Ionia’s tourist development is the construction of a modern, organized and large (in size and possibilities) sport centre around Panthessalikon Stadium sports centre, and the gratis international promotion of the city. This constitutes a comparative advantage against other cities that, like Nea Ionia, don’t have a classic tourist destination profile to promote. The elements that could lead to tourist development should be focused on:

- The staging of special sport events after the Olympics (this is actually happening: European Gymnastics and Volley Championship)

- The promotion the great arched Mycenaean tomb in ‘Kazanaki’ area that could become the ‘heart’ of a visited archaeological site

- The promotion of the local cuisine.

## 5.2 Analysis of the cultural sector

In Nea Ionia most local experts (sample: 20 individuals) believe that the cultural sector has a moderate to low influence in the local economy. Medium economic impact is perceived through the use of the cultural sector as a vehicle for participation in European programmes. Other areas where the cultural sector is reckoned to have an influence, albeit a weak one, are towards GDP growth, unemployment reduction and enhancement of competitive advantage, whereas the least effect is recognised in the creation of an entrepreneurial climate and the attraction of foreign investment in the city (Table 3).

Table 3: Contribution of the cultural sector to economic development

(Likert scale - 1: lowest, 5: highest)

| ###### Factors of contribution | Nea Ionia |
| --- | --- |
| Constitution of the main axis of city participation in European programmes for culture | 2,7 |
| Reduction or minimization of unemployment | 2,3 |
| Support of the economic dynamism of the city through the creation of competitive advantage on the field of culture | 2,2 |
| Creation of higher GDP per capita | 2,0 |
| Production of positive economic effects not only to the city but to the wider community | 2,0 |
| Keeping of the high qualified workforce in the area | 1,8 |
| Growth of the foreign investments in the area | 1,4 |
| Support of the creation of a powerful entrepreneurial climate in the area | 1,3 |
| Average | 2,0 |

Source: CultMark, 2005a.

## 5.3 Factors that constitute advantages of the cultural sector

Nea Ionia is moderate in regard to the specific cultural elements that give an advantage to the city. Most of the specified factors are seen as not particularly important, apart from the existence of private and public cultural organizations with active role in the planning and implementation of cultural activities, which are perceived to support the cultural sector at a moderate degree. Furthermore, the attraction of investments and European funds seems to be quite advantageous factors but not able to create, by their own, a strong advantage for the city. Areas that are regarded as least significant are the existence of museums and art galleries. It is characteristic that all other factors are evaluated very low (Table 4).

Nea Ionia focuses on cultural development, but the major contradiction is that it presents a strong cultural historical background with weak current facilities and even weaker cultural environment. The main focus seems to be on specific cultural events and projects, even if these factors present a low score as advantages (Table 4). International experience shows that both these dimensions are based on the ability and the capacity of each city to provide a strong cultural position, in connection to its ability to satisfy each time the demands and expectations of cultural tourism. This creates the necessity that public and private organizations are appreciated as the top advantage factors of the cultural sector, so that they evaluate the weaknesses of the city, and plan the appropriate policies and actions that enforce Nea Ionia’s cultural position, in order that the ‘final provided good’ has  positive impacts for economic development and competitiveness.

Table 4: Factors that constitute advantages of the cultural sector

(Likert scale - 1: lowest, 5: highest)

| ##### Factors | Nea Ionia |
| --- | --- |
| The existence of private cultural organizations with active participation in planning and implementing cultural activities | 3,2 |
| The existence of public cultural organizations with active participation in planning and implementing cultural activities | 2,7 |
| The existence of a strong and worldwide known historical background | 2,3 |
| The exploitation of European funds for the development and support of cultural investments | 2,3 |
| The existence of conservatoires and/or orchestras with worldwide fame | 1,8 |
| The existence of cultural heritage buildings with worldwide fame | 1,8 |
| The holding of major cultural events (festivals, exhibitions etc) with worldwide fame | 1,8 |
| The existence of qualified and specialized work force in cultural organisations | 1,8 |
| The existence of strong commercial activities (businesses that focus on the production of cultural products) | 1,7 |
| The existence of graduate or postgraduate programmes on cultural studies | 1,5 |
| The existence of theatres and/or operas with worldwide fame | 1,3 |
| The existence of famous historical personalities related to the city | 1,2 |
| The existence of museums (archaeological and/or modern) with worldwide fame | 1,2 |
| The existence of large cultural art galleries with worldwide fame | 1,2 |
| ##### Average | 1,8 |

Source: CultMark, 2005a.

#### 5.4 The definition of the vision of Nea Ionia

Nea Ionia envisages a city that is economically robust, socially balanced and pays due respect to both the natural and the cultural environment. Experts regard that a well planned development, which takes care of the environmental problems (including traffic) and provides the necessary cultural infrastructure (museums, theatres, galleries or other spaces to house culture), will support further development of the city as a tourist destination and attraction pole. The local cultural characteristics of the people (mainly refugees for Asia Minor), the beauty of the natural environment of the wider area, and the available sport infrastructure (mainly developed for the 2004 Olympics), constitute some of the main assets of the place (CultMark, 2005a).

Regarding the factors that contribute to the accomplishment of the city vision, those that score high are two: the participation in European development programmes in cooperation with other cities, and the acceptance of the vision by the local community. The diagnosis and evaluation of the distinctive characteristics of each development sector for Nea Ionia, is a crucial factor that could contribute to the accomplishment of the vision. Also the significance of developing partnerships between local authorities with the universities and citizens, in the context of a cooperative marketing strategy, is very crucial in order that the vision of the city is satisfied. Also, the ability of local authorities to adopt and implement innovative policies presents a quite high degree of importance (Table 5).

Table 5: Factors that contribute to the accomplishment of vision

(Likert scale -: 1: lowest, 5: highest)

| Factors | Nea Ionia |
| --- | --- |
| The participation to specific European development programmes in co-operation with other cities | 3,8 |
| The understanding of the community that the vision of the city is a common interest | 3,5 |
| The planning and the development of partnerships between the local authorities and the citizens | 3,3 |
| The adaptation and the implementation of new innovative promotional policies by local authorities | 3,2 |
| The diagnosis and the evaluation of city’s distinctive characteristics in each development sector | 3,0 |
| The planning and the development of partnerships between the local authorities and the and the academic or research centres | 3,0 |
| The representation of common interests for city development by the local authorities, the enterprises and the community | 3,0 |
| The level of capacity and the level of knowledge of the local authorities to plan and to implement development policies | 3,0 |
| The planning and the implementation of particular urban development plan | 2,8 |
| The development of a systematic collection of data and information supporting the decision making process | 2,8 |
| The identification of particular main development goals | 2,5 |
| The planning and the development of partnerships between the local authorities and the business community | 2,5 |
| The analysis of city’s internal and external environment (based on particular methods, such as SWOT analysis) | 2,0 |
| Average | 3,0 |

Source: CultMark, 2005a.

#### 5.5 The definition of the image of Nea Ionia as a ‘final provided good’

The image of Nea Ionia comprises of two elements, the traditional and the modern. On the one hand, it is a city that seeks to keep its links with its distinctive traditions and cultural heritage, and, on the other hand, it strives to become modern and economic robust, confronting the same problems of urbanisation that most Greek cities face (i.e. congestion, pollution, etc.). Local experts support that the city has a high level of natural environment quality (77,8%, i.e. the added percentages of columns 4 and 5), of local community hospitality (66,7%) and of provision of open and green spaces (55,5%).

The combination of the traditional and modern image is also supported from the responses of tourists (CultMark, 2004a). Most of the tourists believe that Nea Ionia constitutes a strong ‘attraction tourism pole’ (69,5%), is a destination which provides the opportunity to develop several kinds of tourism activities (65%), and combines a modern and traditional image which is acknowledged worldwide (50,9%).

Combining the results above and considering the particular strategies that Nea Ionia wants to develop, its final provided good is based on tourism with the following three dimensions: culture, sport and food activities (Figure 1).

The main question relates to the capacity of Nea Ionia to support and promote this good effectively to the selected target markets. The particular combination is very difficult, since it requires particular promotional policies and, consequently, particular sub-promotional channels, but it offers the opportunity for a multidimensional good. The creation of specific promotional packages will be a very good action, but it depends on the identification of the particular tourist markets that Nea Ionia wants to attract.

# Archaeological Tourism

Mycenaean tomb, Neolithic settlements of Sesklo and Dimini, Archaeological Museum, Glafyra Acropolis

# Sport Tourism

Panthessalikon Stadium, Basdekio Stadium, 5x5 soccer fields, football grounds and many more sports facilities.

# A multi -dimensional good,

With specific particularities in planning and implementing promotional policies

With specific difficulties in target markets’ evaluation

Main strategy: Focus

Main question: Does the city have the capacity to offer and to support this good effectively?

# Food Tourism

Traditional ‘tsipouradiko’, traditional Minor Asia cuisine.

Figure 1: Shaping the final provided good of Nea Ionia

5.6 The definition of the appropriate target markets in Nea Ionia

The ‘Promotional and Distributional “Maps” Report’ (CultMark, 2004a) selected the target markets that Nea Ionia can distribute and finally promote its image. In all CultMark places the selected target markets were separated into two levels of activity: the microeconomic and the macroeconomic one. At the first level, the selected target markets concern the internal city environment (residents, enterprises, organisations, local authorities, groups with special needs and characteristics, minorities, decision makers, unions, universities, research centres etc). All these groups are potential ‘consumers’ of the final provided good, and all of them want to satisfy their needs and perceptions. The most important point is to identify which of these target markets are profitable for the city, i.e. which target markets are interested for the final provided good. In the case of Nea Ionia the focus is on the following internal potential target markets:

Enterprises that relate to the multidimensional character of the final provided good (arts, sport centres, restaurants, hotels, travel agencies etc). The role of these markets is crucial, since there are representatives of Nea Ionia’s image. These enterprises should provide the best quality of services satisfying the demands and the perceptions of the potential target markets. These enterprises are also ‘consumers’ of what Nea Ionia offers.

Decision makers, authorities, organisations that relate to the multidimensional character of the final provided good (cultural organisations, public enterprises, tourist associations, universities, etc). The role of these groups is very important, since it is related with the decision making process.

Residents: This group is the key factor in order that a local community effectively adopts and performs a place marketing policy. Residents are both consumers and providers of the distinctive goods that Nea Ionia offers.

At the macroeconomic level, the final provided good has to be supported and promoted at national, European and international level. The identification of the selected target markets is more difficult and requires a strategic development process. Taking into account that Nea Ionia is a small area that decides to promote a multi-dimensional image, the selection of the image receivers has to be done very carefully. The existence of three tourist dimensions in the creation of the final good requires the identification of separate groups for each dimension, and also the creation of common promotional packages where the ‘consumer’ could combine activities through this package. More particularly:

Tourists with special interests at national, European or international level: This target market consists one of the most important and profitable for Nea Ionia. The procession of this market is difficult, since in order to attract people with special interests, the city should have the ability to satisfy their demands offering high quality of services and combine innovative promotional packages. The attraction at European level is even more difficult, since it is related with a continuous representation of Nea Ionia’s distinctive image at the international tourism market.

Cultural, tourist and sport organizations at national and European level (museums, galleries, exhibitions etc): The representation of these organisations is crucial. It is related with the international promotion of Nea Ionia and its relevant worldwide acknowledgement. Nea Ionia should attract national and European organisations in order to host and organise special events, which is the most important goal of its marketing orientation. Especially in the case of sport, the new facilities as an Olympic municipality offer the opportunity to develop special sport events.

  - The identification of  the distribution channels

The identification of the distribution channels concerns the transmission of the final provided good, the ‘message’ of the city to the potential target markets. Two kinds of geographical distribution channels are identified: the internal and the external, relating to the separation of the aforementioned selected target markets. ‘Level A’ concerns some generic distributors that constitute also target markets at national, European and international level, and ‘Level B’, concerns the selection of distributors relating to the multi- dimensional character of the final provided good.

The management of these distribution channels concerns the rapid and effective transmitting of the ‘final provided good’ to the potential target markets. Each of the distributors has to be able to inform and to propose Nea Ionia as a destination with multi-dimensional tourist character, able to satisfy the demands and the perceptions of the selected groups. The separation of the distributors according to the character of the provided good is an important process and it is related to the effectiveness of the distribution. This separation also satisfies the Nea Ionia’s effort to become known for specific tourist activities focusing on culture, sport or food. Each dimension is working in two levels. The first level requires the planning and the performance of specific actions per sector. At the second level all the sectors participate to the implementation of common activities. The primary goal is to promote and to distribute Nea Ionia as a ‘multi-tourist destination’, but this goal is very difficult to be achieved quickly in relation to the acknowledgement at European or international target markets. Thus, it is proposed that city planners and marketers focus primarily on the effective promotion at national level and then move to activities at European and international level.

In both these channels the feedback procedure plays a crucial role. The effective contribution of this process requires the existence of alternative scenarios and tactics in order to be faced problems that might rise. Finally the whole distribution process presupposes the existence of a promotional office with specialized workforce.

5.8. Proposed strategies and tactics

The identification of the strategies should satisfy the development objectives of the place. Kotler et al (1993, 1999), pointed out two crucial questions concerning strategies formulation: a) what advantages do we possess that suggest we can succeed with the strategy and b) do we have the resources required for successful implementation of the strategy. Concerning the evaluation of the most appropriate strategies, Porter (1980) proposed two basic strategies that could be implemented in the case of city/ place marketing: a) differentiation strategy and b) focus strategy. The first strategy is related to the awareness of the competitive advantages and the uniqueness of the place, while the second one focuses on a specific target market in which the place should cover and satisfy particular needs. Deffner and Metaxas (2006), proposed two additional strategies, those of penetration strategy and co-operative marketing strategy. At the first one, the place image penetrates into a new target market promoting and supporting the local goods that already exist, while the second strategy requires the planning and the implementation of promotional actions, through the representation of common interests of place internal actors.

In the case of Nea Ionia the main proposed strategy is the focus one. Τhe implementation of this strategy relates neither to large metropolitan centres, nor large urban centres, but to small and well organized places which focus on the provision of their image to particular target markets aiming to increase their market share on these markets. The effectiveness of this strategy requires the identification of city’s major strengths (answering the question: which is our competitive distinctive characteristic?) and then the provision of this characteristic to the selected target markets.

The main tactic refers to the correlation between the diagnosis of the specific demands and perceptions of the distinctive selected target market and the level of capacity of the place to satisfy these in the highest degree.

Taking into consideration that the vision of Nea Ionia is based on the identification of distinctive characteristics and the strong cultural identity, a focus strategy could satisfy the vision and the development objectives for the following reasons:

a) the city tries to increase its market share to specific tourist markets at national level and to penetrate in the same markets at European and international level. Thus, the enforcement of its tourist economy is based on the effective attraction of these target markets and the total satisfaction of their needs and perceptions,

b) the creation of a competitive advantage based on the analysis and the evaluation of these target markets. Nea Ionia should focus on their particularities, in order to plan and to perform the appropriate actions that secure the successful development of its promotional policy,

c) the vision of Nea Ionia is to become an attraction pole, promoting to the potential target markets a multi-dimensional image. The implementation of a focus strategy provides the opportunity to the city to get knowledge and experience through this process that allows, at the same time, the satisfaction of its development objectives, and

d) the implementation of a focus strategy is closer to the vision and the objectives of the city, since it is a strategy that is proposed for small cities, with low level of reputation, low ability to implement a variety of promotional policies and also an internal weakness in developing effective partnerships between city’s internal actors.

6. The Methodology of the CMPP

6.1 The implementation of the Critical Path Model

The implementation of the CMPP of Nea Ionia has a temporal horizon of 410 ‘working’ days. The character of the Pilot Programme ‘Promotion Methodology’ is strategic and could be characterized as a ‘project’, in a whole process of the CMPP. The method used in the research in order to set up a particular time limit for the promotion methodology is based on the ‘Critical Path Method Analysis’ (Aravantinos, 1987/1994: 78-9; Nokes et al., 2003). CPM is based on the identification of three basic factors:

- Hierarchical Presentation of activities. This characterizes each activity with a particular name. The presentation of the activities is hierarchical. The important thing is to include all the appropriate actions in order the City Marketing Pilot Plan, to become a useful database, for the implementation of the City Marketing Final Plan.

- Immediate predecessor: This presents those activities (one or more) that have to be finished first and then the present activity to take place. This view has major significance for the project, since it allows estimating which of the activities are core (have to be done first and any delay on their implementation affects the total planning of the project), and which are secondary (they could be implemented at the same time with other activities)

- Temporal horizon: The existence of a specific temporal horizon is very important for each step and of course for the whole project. Time horizon is closely related to the satisfaction of city’s objectives in the frame of a specific time planning. Time planning also related with the existence of alternative scenarios in case that some actions have to be changed and replaced by others.

CPM includes the following four main phases of the project.

  - PLANNING: In this phase, the city decision makers and the local actors have to plan and prepare all those actions that related with the promotion and the support of Nea Ionia multidimensional good. The first step is the creation of the Executive Management Group (EMG), which will take the overall responsibility to plan and to perform the City Marketing Pilot Plan for Nea Ionia. Each part of this model has been separated in particular steps of planning phase, in order to become a guideline for the EMG. The crucial point is that the effectiveness of the whole project based on the phase of Planning. Any kind of steps delay, means delay of the following phases and consequently delay of the whole project.  The overall temporal horizon of this phase is 120 ‘working’ days. The primary actions need 65 days and the secondary actions 55 days.

  - PROGRAMMING: In this phase, the EMG has the main responsibility of programming, a number of core actions that have take place before the phase of implementation. These actions concern the building of the communication process, the preparation of focus group analysis, the positioning of the final provided good of Nea Ionia to distributors and finally the development of a mini-guide seminar to all participants and the selected distributors. This phase requires brainstorming methods and discussions, for the continuation of the CMPP. The temporal horizon of this phase is 60 ‘working’ days. The primary actions need 45 days and the secondary actions 15 days.

  - IMPLEMENTATION: This phase is characterized by the existence of promotion process, almost in all of the actions. In particular this phase is the promotion phase. The core actions related with the focus groups analysis, the primary research, the improvement or the creation of the website, and finally the implementation of a variety of advertising activities on Media, magazines, newspapers, etc. In addition, the participation of Nea Ionia in two events (i.e. exhibition) in national and European level, is also proposed. The implemented actions it is crucial to be supported by a good and effective group of Public Relations. Finally the project proposed some additional actions, such as the creation of a TV programme (documenter), the creation of info-kiosks, the production of DVD, CD-ROM and Videos. All the promotion activities of this phase are on a continuing process. The temporal horizon of each is a potential time and mainly concerns the time of scheduling these actions. The phase of implementation is the longest of the pilot project: it takes 175 ‘working’ days. The primary actions need 65 days and the secondary actions 110.

- EVALUATION – FEEDBACK: This phase is related with the evaluation of the actions that take place in the phase of the implementation. The main aim of this final phase is EMG to come up to the final decisions in order to continue the programme by preparing the City Marketing Final Plan, or to reject the whole effort. So, it’s very important for EMG, to analyse all the available resources and evaluate in which phases of the project is needed to become changes, reductions, reconstructions etc. One very important point, of this phase is that EMG has to prepare a very functional City Marketing Final Plan, with specific actions and with main concerns to support and promote the distinctiveness of Nea Ionia. The umbrella of this process is the vision of the city and the major development objectives. EMG needs to implement a plan flexible, innovative, and according to the evidence and the guidelines of the City Marketing Pilot Plan. In other words it is necessary to provide an official plan that faces the demands of the potential target markets on the one hand and city’s development aims on the other. The whole phase needs 56 ‘working’ days: 46 for primary actions and 10 for secondary ones.

Table 6 and Figure 2 present for instance the proposed steps of the first phase of Critical Path Method (Planning), which is common for all the places of CultMark project, i.e. for the case of Nea Ionia.

Table 6: The steps of the Planning phase for the CMPP of Nea Ionia

|  | ACTIVITIES | ACTIVITY CODE | IMMEDIATE PREDECESSOR | TIME (days) |
| --- | --- | --- | --- | --- |
|  | 1st phase: PLANNING (1-12) |  |  |  |
| 1 | Composition of the Executive Management Group (EMG) and the groups that participate in each action (Morrison model: partnership and people) | A | - | 5 |
| 2 | Analysis of the competition at the regional and national level | B | A | 10 |
| 3 | Analysis of the competition in the Balkans and at the European level | C | A | 15 |
| 4 | Identification of the ‘final provided good’ – The ‘multidimensional good’ of the city (Morrison model: product) | D | A | 10 |
| 5 | Creation of tourism, cultural and sports ‘packages’ (Morrison model: packaging pricing) | E | D | 15 |
| 6 | Re- Evaluation of the selected target markets based on their characteristics analysis– Choose the appropriate sample (internal environment) | F | D, E | 10 |
| 7 | Re- Evaluation of the selected target markets based on their characteristics analysis– Choose the appropriate sample (external environment) | G | D, E | 10 |
| 8 | Evaluation and selection of the distributors for each part of the ‘final provided good’ (Morrison model: place) | H | F, G | 10 |
| 9 | Evaluation of the selected strategies and tactics per target market (internal environment) | I | F | 10 |
| 10 | Evaluation of the selected strategies and tactics per target market (external environment) | J | G | 10 |
| 11 | Evaluation and final selection of the promotional means (Morrison model: promotion) | K | D, E, I, J | 10 |
| 12 | EMG meeting 1 | L | K | 5 |
|  | End of the first phase |  |  | 120 |

Figure 2: Critical Path Diagram of the 1st phase

C

15 (15+5 = 20)

START

10 (10+5=15)

15 (15+15=30)

10 (10+30=40)

10 (10+40=50)

A

D

E

F

I

5

10 (10+50=60)

B

G

H

K

10 (10+5=15)

10 (10+30=40)

10 (10+40=50)

J

L

5 (5+60=65)

10 (10+40=50)

# 6.2 The proposed model of ‘8ps’

In all partners’ cases, the study used, in order to set up a ‘production procedure’, two models from the world of marketing world. The first one is the generic and very popular model of ‘4ps’ (Kotler and Armstrong, 2005): product, price, place and promotion. The second one is more complicated and it is called the ‘8ps’ model (Morrison, 1989/2001): product, partnership, people, packaging, programme, place, price, promotion. From the two models, the study selects the model of ‘8ps’ as the most appropriate. The ‘8ps’ model is mainly used for tourist destinations, which have as their main axes travel and hospitality.

Figure 3: Place Marketing ‘8ps’ model by Morrison

- PRODUCT OR SERVICE (GOOD)

- PARTNERSHIP

- PEOPLE                                                                                             PLACE   MARKETING

- PACKAGING                                                                                           STRATEGIC

- PROGRAMMING                                                                                            MIX

- PLACE (Distribution channels)

- PRICE

- PROMOTION

The 8ps for Nea Ionia focus on the parameters presented in Table 7.

Table 7: The ‘8ps’ model for Nea Ionia

| ###### 8Ps | Nea Ionia |
| --- | --- |
| PRODUCT (GOOD) | A multiple tourism good based on heritage, sport and food’, a combination of distinctive characteristics that characterised the city. |
| PARTNERSHIP | The study proposes three levels of partnerships for Nea Ionia: a) partnerships with actors and decision makers into place environment b) in regional level and c) in national and European level. These actors concern: local and regional authorities, enterprises, cultural organizations, industrial and commercial associations, chambers of commerce and industry, food organisations, tourists agencies, universities and research centers, EU cultural and sports organizations, environmental associations and residents |
| PEOPLE | Focus on two dimensions: a) The ‘Human resources management’ process. Referring to human resources management for visitors’ attraction, Swarbrooke (1995/2002: 244) supported that it is concerned with obtaining, organizing, training, motivating and rewarding the people needed by the organization so that they can perform in a way which allows the attraction to meet the needs of customers and b) the citizens’ contribution to the city’s development. The citizens of a location have been recognized as one of the most important internal target markets (actors) of a city’s environment. According to Woolley (2000) ‘local people are the key to urban vitality’. McIntosh et al. (1995) used the term ‘motivation’ supporting that the citizens have to be motivated in order to develop actions or to participate in decision analysis procedures, i.e. the case of Winterhur in Switzerland (Ringli, 1997), or to express their opinions on the implementation of particular issues which concern cultural activities, tourism programmes or international events (i.e. festivals, Hanefors 2000; Yeoman et al., 2004) |
| PACKAGING | The proposed packages are: - In CULTURE –HISTORY –NATURE [Archaeological tourism package (Karla, the Neolithic settlements of Sesklo and Dimini - Nea Ionia and the prefecture of Magnesia), Escorted tours package (Nea Ionia and the rest Thessaly region), ‘Places of Spirit’ (Nea Ionia and the rest of Magnesia and Thessaly) Nature tourism packages focus on the development of ‘alternative forms of tourism’] - In FOOD-LOCAL CUISINE (Tsipouradika package, special and traditional cuisine) - In SPORTS (‘Panthesalikon package’, ‘Preparation Teams’ from Greece and Europe, Summer and winter sports activities’) - In EVENTS (common package for all CultMark places) [Cultural, food and sports events] - In CONVENTION AND CONFERENCES MEETING (common package for all CultMark places) [in culture, food and sports] All packages have particular duration and is applied to specific target markets |
| PROGRAMMING | Programming is a very close related process to packaging. Actually is the process that completes the ‘Successful Provided Package’. Programming is based on the existence of ‘Available Time’ of the visit, of the event, and any kind of activity that the potential target market spend into city’s environment. Programming has an ‘organized dimension’. In other words we talk about Effective Time Management, since each of the provided packages has to be planned and also programmed in such way, that will provide the ability of timing to the potential target markets, in a specific and limited time that they have, in order to receive the maximum of the offering city’s services. |
| PLACE (Distribution) channels) | Each of the distributors has to be able to inform and to propose Nea Ionia as a destination with multi-dimension tourism character, able to satisfy the demands and the perceptions of the selected groups. The separation of the distributors according to the character of the provided good, is an important process and its related to the effectiveness of the distribution. This separation also satisfies the effort that Nea Ionia to become known for specific tourism activities focusing in culture, in sports or in food. Each dimension is working in two levels. First separately. This level requires the planning and the performance of specific actions per sector. Secondly all the sectors participate to the implementation of common activities. On this point we have to mention that the primary goal is to promote and to distribute Nea Ionia as a multi-tourism destination’, but this goal is very difficult to achieved quickly concerning mainly the acknowledgement of the European or international target markets. |
| PRICE | The identification of pricing concerns all the services that Nea Ionia provides to the potential target market. This is the general option of pricing and something that concerns all the participants to the provision of these services. The second option related with the pricing of the proposed packages. The EMG has to identify what will be the final cost of each package, taking into consideration the relationship between pricing and quality. This is very important since it is related with the implementation of the strategies that we proposed, in order the final provided good to be posit effectively in the market that each place wish to penetrate. The third option is related with the promotion costs of the multidimensional good. For instance and according to the CPM, Nea Ionia has to run a number of advertising activities (electronic and printed media etc.). For each of these means it is necessary to exist a particular cost budget (i.e media: the scenario, actors, timing – TV programme zone, frequency, copyright, etc). The study proposes the creation of a particular cost-budget analysis plan that will include all the promotion activities of each place in an annual base in order the whole cost to be covered by the Total City Marketing Budget of Nea Ionia. |
| PROMOTION | Proposed promotional means: Television, Internet, Magazines, Newspapers, Newsletters, Brochures, Prospectus, Direct sales, Exhibitions fairs and events etc. |

Source: Source: CultMark, 2005b

# 7. Conclusions

The main aim of this paper was to present the various dimensions of the City Marketing Pilot Plan (CMPP) for Nea Ionia, Magnesia, Greece. The data for this paper were provided by the INTERREG IIIc CultMark project. The innovative characteristics of this project are reinforced by the use of the two concepts of ‘creativity’ and ‘branding destination’. The actions relating to place marketing, hallmark events and branding focus on the concept of creativity. Creativity is a dynamic tool for urban innovation and imaginative action, focusing on culture, and contributing to the success of various contexts (smaller cities, hidden resources in capitals, non-innovative setting). Some of the foundations of creativity are: organizational culture, fostering strong local identity, networking and associative structures (Landry, 2000).

Τhe city's brand helps to increase it status as tourist destination, residential or business location. Branding is associated primarily with economic value, but also with symbolic values, since it constitutes a strategy to provide cities with an image and a cultural meaning. Branding indicates the need for individuality and emotional connection with the environment in the context of globalisation. Cities should have depth, originality, and a distinct character though the materialisation of choice, diversity, and distinguishing features (Landry, 2000). Thus, branding contributes to the construction of local identity.

The CMPP is based on the Strategic Planning process, always starting from the identification of the city’s vision (focusing on its branding) and the primary urban development objectives that have to be satisfied.  Thus, the CMPP has a strategic character, based on its structure in connection to the identification of the most appropriate promotion methodology that provides the opportunity to the city to examine and evaluate some first results of the implementation of place marketing actions. A very important factor is that the CMPP has to take place in a particular temporal horizon (410 ‘working’ days), and during this period city’s actors, marketers and decision makers, have to collect and evaluate valuable information that is related with the development, or the change, of the CMPP structure either as a whole, or its parts. The CMPP aims to establish the main axes for the preparation and the development of the City Marketing Final Plan.

References

Aravantinos, A. (1984/1998) Urban Planning: Towards a Sustainable Development of the Built Environment, Athens: Symmetria. [in Greek]

Ashworth G. J. and Voogd H. (1990) Selling the City: Marketing Approaches in Public Sector Urban Planning, London:  Belhaven Press.

Ashworth, G. J. and Voogd, H. (1994) ‘Marketing and place promotion’, in Gold and Ward.

Avraham, E. (2000) ‘Cities and their news media images’, Cities, vol. 17, no.5 pp. 363-370.

Avraham, E.  (2004), ‘Media strategies for improving unfavorable city image’, Cities, vol. 21 (6): 471-479.

Bramwell, B. (1998) ‘User satisfaction and product development in urban tourism’, Tourism  Management, 19 (1), pp. 35-47.

Buhalis, D. (2000) ‘Marketing the Competitive destination of the future’ Tourism Management, 21, pp. 97- 116.

Chaudhary, M. (2000), India’s image as a tourist destination- a perspective of foreign tourists, Tourism Management, 21 pp. 293-297.

Choi, M, W., Chan, A., and Wu, J. (1999) ‘A qualitative and quantitative assessment of Hong Kong’s image as a tourist destination’, Tourism Management, 20, pp 361-365.

CultMark (2004a) Final Provided Good Report, INTERREG IIIc.

CultMark (2004b) Promotional and Distributional ‘Maps’ Report, INTERREG IIIc.

CultMark (2005a) Cultural Data Report, INTERREG IIIc.

CultMark (2005b) City Marketing Pilot Plan of Nea Ionia, INTERREG IIIc.

Deffner A. and Metaxas T., (2003) ‘The interrelationship of urban economic and cultural development: The case of Greek museums’ (CD-ROM) paper presented to the 43rd ERSA Congress "Peripheries, centers, and spatial development in the new Europe", University of  Jyväskylä, Jyväskylä, Finland

Deffner A. and Metaxas T. (2006) ‘Place Marketing: Preparing a Place Marketing Pre-Plan in

the case of Nea Ionia, Magnesia, Greece’, in the Proceedings of the 2nd International Meetings Industry Conference Marketing Destinations and their Venues ACS Halandri forthcoming.

Duffy, H. (1995) Competitive Cities: Succeeding in the Global Economy, London: Spon.

Gold J.R. and Ward S. V. (eds) (1994) Place Promotion: The Use of Publicity and Marketing to Sell Towns and Regions, Chichester: Wiley.

Goodwin, M. (1993) ‘The City as Commodity: The Contested spaces of urban development’, in Kearns and Philo (eds).

Hafenors, M. (2000) ‘The Locals-Local Knowledge, Participation, and Identity’, in L.L. Mossberg (ed.) Evaluation of Events: Scandinavian Experiences, Cognizant Communication Corporation, pp. 47-62.

Hall T. (1998/2001) Urban Geography, Routledge, London and New York.

Hope, A.C., and Klemm, S.M. (2001), ‘Tourism in difficult areas revisited: the case of Bradford’, Tourism Management, 22, pp. 35-47.

Kearns G. and Philo C. (eds) (1993) Selling Places: The City as Cultural, Capital, Past and Present, Oxford: Pergamon.

Konken, M. (2004) Stadtmarketing: Kommunikation mit Zukunft, Messkirch: Gmeiner-Verlag.

Kotler P., Armstrong, G. (2005) Principles of Marketing, Englewood Cliffs: Prentice Hall. (11th ed.)

Kotler P., Asplund C., Rein I. & Haider H.D. (1999). Marketing Places Europe: Attracting Investments, Industries and Visitors to European Cities, Communities, Regions and Nations, Harlow: Financial Times/ Prentice Hall.

Kotler P., Rein I., Haider H.D. (1993) Marketing Places: Attracting Investment, Industry and Tourism to Cities, Regions and Nations, New York: Macmillan.

Landry, C. (2000) Creative City: A Toolkit for Urban Innovators, London: Earthscan Publications.

McIntosh R.W., Goeldner C., Ritchie J.R.B. (1995) Tourism Principles, Practices, Philosophies, Wiley, New York.

Meler, M., and Ruzic, D. (1999) ‘Marketing identity of the tourist product of the Republic of  Croatia’, Tourism Management, 20, pp.635-643.

Metaxas T., (2003) ‘The image of the city as a ‘good’: The creation of a city’s promotional package through a strategic framework analysis of City Marketing procedure’ in Beriatos E. et al (eds) Sustainable Planning and Development, Wessex Institute of Technology and Dept. of Planning and Regional Development (Univ. of Thessaly), pp. 427- 438.

Misiura, S (2005) Heritage Marketing, Oxford: Elsevier Butterworth-Heinemann.

Morgan, N., Pritchard, A., and Pride, R. (eds) (2002/2004) Destination Branding: Creating the Unique Destination Proposition, Oxford: Elsevier Butterworth-Heinemann.

Μorrison, A. (1989/2001) Hospitality and Travel Marketing, Delmar Publishers.

Murphy P., Pritchard M.P and Smith B., (2000) ‘The destination product and its impact on traveler perceptions’ Tourism Management, vol. 21, no.1, pp. 43-52.

Nokes, S., Greenwood, A., Major, I., Allen, D., Goodman, M. (2003) The Definitive Guide to Project Management: Every Executives Fast-track to Delivering on Time and on Budget, Pearson Education.

Oppermann, M. (1996) ‘Convention destination images: analysis of association meeting planner’s perceptions’, Tourism Management, vol. 17, no.3, pp. 175-182.

Porter, M. (1980) Competitive Strategy: Techniques for Analysing Industries and Competitors, N.Y: Free Press.

Patteeuw, V./ Urban Affairs (eds) (2002) City Branding: Image Building and Building Images, Rotterdam: NAI Publishers.

Ringli H., (1997) ‘Plan-making in the Zurich region’ in Healy P., Khakee., A., Motte A., Needham B. (eds) Making Strategic Spatial Plans, London: UCL Press.

Short R.J and Kim Y-H, (1998), ‘Urban Crises / Urban representations: selling the city in difficult times’, in T. Hall and P. Hubbard (eds) The Entrepreneurial City, J. Wiley and Sons.

Snaith T. and Haley A. (1999) ‘Resident’s opinions of tourism development in the historic city of York, England’, Tourism Management, vol.20, pp. 595-603

Swarbrooke J. (1995/ 2002) The Development and Management of Visitor Attractions, Oxford: Elsevier Butterworth-Heinemann.

Tsegenidi, K. (2001) City Marketing: From the German Experience to the Greek Reality, Diploma Thesis, Department of Planning and Regional Development, University of Thessaly, Volos.

Urban F. (2002) ‘Small Town, Big Website? Cities and their Representation on the Internet’, Cities, vol.19, pp. 49-59.

Ward S. (1998). Selling Places: The Marketing and Promotion of Towns and Cities 1850-2000 London: E. & F. N. Spon/ Routledge.

Wooley H. (2000) ‘Town centre management awareness: an aid to developing young people’s citizenship’, Cities, vol. 17, pp. 453-459.

Yeoman, I. Robertson, M., Ali-Knight, J., Drummond, S., McMahon-Beattie, U. (2004) Festival and Events Management: An International Arts and Culture Perspective, Oxford: Elsevier Butterworth Heinemann.

Zerres, M. and I. (eds) (2000) Kooperatives Stadtmarketing: Konzepte, Strategien und Instrumente zur Erhöhung der Attraktivität einer Stadt, Stuttgart: Kohlhammer.

The scientific support of CultMark is provided by the Laboratory of Tourism Planning Research and Policy (LATOUPREP), Department of Planning and Regional Development, University of Thessaly. The director is Alex Deffner, Assistant Professor of Urban and Leisure Planning, and the members are Pashalis Arvanitidis (Lecturer), Nick Bogiazides (Αdjunct Assistant Professor), Theodore Metaxas (Adjunct Lecturer), Christos Liouris, Penelope Melidou, and Christina Vlahopoulou. Sections 5.2 and 5.3 are based on the Cultural Data Report (2005) which was elaborated mainly by P. Arvanitidis with the initial help of C. Liouris and P. Melidou.