## Gantt Chart
Preparatory Action: European Partnerships on Sport
Europe is our Playground
[5 empty] | Start Date: |  |  |  |  | 2014-02-17 |  |  |  |  | End Date: |  |  | 2015-02-16
|  | Year |  |  | 2014 | [11 empty] | 2015
|  | WP Title: |  | List of delivarables: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | Partner Involved
1 | WP 1 | Coordination and Management | 1.1 | Project Coordination and Financial Management | [14 empty] | GR
|  |  | 1.2 | Project Meetings | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL
2 | WP 2 | Network Establishment, Recording of stories | 2.1 | Multilingual Webpage | [14 empty] | GR | bar: 2014 5 to 2014 6
|  |  | 2.2 | Local points promoting traditional games and sports | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 4 to 2014 11
|  |  | 2.3 | Recording of verbal stories from older people | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 4 to 2014 6
|  |  | 2.4 | Internet Games creation and activation | [14 empty] | GR | bar: 2014 7 to 2014 8
|  |  | 2.5 | Main Research: Traditional Games and Sports selection and set of acceptable common rules | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 3 to 2014 6
3 | WP 3 | Organization of events demonstration | 3.1 | Demonstration Event/s of Traditional Games/Sports | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 7
|  |  | 3.2 | Exhibition/s of Items of Traditional Games and Sports. Workshops. | [14 empty] | GR | bar: 2014 7
4 | WP 4 | Organizing Competitions | 4.1 | Amateur Photo Competition | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 10 to 2014 11
|  |  | 4.2 | Students Essay Competition | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 10 to 2014 11
|  |  | 4.3 | Painting Competition | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 10 to 2014 11
5 | WP 5 | Communication and Dissemination (Information and Publicity) | 5.1 | Brochures | [14 empty] | GR | bar: 2014 5 to 2014 9
|  |  | 5.2 | Newsletters, Press releases and media publications | [14 empty] | GR | bar: 2014 3 to 2015 2
|  |  | 5.3 | Press Conferences | [14 empty] | GR | bar: 2014 3; 2014 7; 2015 2
|  |  | 5.4 | International Conference | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 7
|  |  | 5.5 | Publication of WP4 collection and WP 3 (events) moments | [14 empty] | GR | BG1 | BG2 | BG3 | D1 | D2 | SE | PL | bar: 2014 12 to 2015 2
Note on T7: Dimofelia
Note on T9: Dimofelia
Note on T10: Dimofelia
Note on T12: Dimofelia
Note on T13: Dimofelia
Note on T15: Dimofelia
Note on T16: Dimofelia
Note on T17: Dimofelia
Note on T21: Dimofelia
Note on T22: Dimofelia
Note on U7: Municipality of Bansko
Note on U9: Municipality of Bansko
Note on U10: Municipality of Bansko
Note on U12: Municipality of Bansko
Note on U13: Municipality of Bansko
Note on U15: Municipality of Bansko
Note on U16: Municipality of Bansko
Note on U17: Municipality of Bansko
Note on U21: Municipality of Bansko
Note on U22: Municipality of Bansko
Note on V7: Varna Municipality
Note on V9: Varna Municipality
Note on V10: Varna Municipality
Note on V12: Varna Municipality
Note on V13: Varna Municipality
Note on V15: Varna Municipality
Note on V16: Varna Municipality
Note on V17: Varna Municipality
Note on V21: Varna Municipality
Note on V22: Varna Municipality
Note on W7: Friends of the Museum - Rousse
Note on W9: Friends of the Museum - Rousse
Note on W10: Friends of the Museum - Rousse
Note on W12: Friends of the Museum - Rousse
Note on W13: Friends of the Museum - Rousse
Note on W15: Friends of the Museum - Rousse
Note on W16: Friends of the Museum - Rousse
Note on W17: Friends of the Museum - Rousse
Note on W21: Friends of the Museum - Rousse
Note on W22: Friends of the Museum - Rousse
Note on X7: Municipality of Nürnberg
Note on X9: Municipality of Nürnberg
Note on X10: Municipality of Nürnberg
Note on X12: Municipality of Nürnberg
Note on X13: Municipality of Nürnberg
Note on X15: Municipality of Nürnberg
Note on X16: Municipality of Nürnberg
Note on X17: Municipality of Nürnberg
Note on X21: Municipality of Nürnberg
Note on X22: Municipality of Nürnberg
Note on Y7: Griechische Kulturstiftung in Berlin
Note on Y9: Griechische Kulturstiftung in Berlin
Note on Y10: Griechische Kulturstiftung in Berlin
Note on Y12: Griechische Kulturstiftung in Berlin
Note on Y13: Griechische Kulturstiftung in Berlin
Note on Y15: Griechische Kulturstiftung in Berlin
Note on Y16: Griechische Kulturstiftung in Berlin
Note on Y17: Griechische Kulturstiftung in Berlin
Note on Y21: Griechische Kulturstiftung in Berlin
Note on Y22: Griechische Kulturstiftung in Berlin
Note on Z7: Strömstads Kommun
Note on Z9: Strömstads Kommun
Note on Z10: Strömstads Kommun
Note on Z12: Strömstads Kommun
Note on Z13: Strömstads Kommun
Note on Z15: Strömstads Kommun
Note on Z16: Strömstads Kommun
Note on Z17: Strömstads Kommun
Note on Z21: Strömstads Kommun
Note on Z22: Strömstads Kommun
Note on AA7: Municipality of Warsaw
Note on AA9: Municipality of Warsaw
Note on AA10: Municipality of Warsaw
Note on AA12: Municipality of Warsaw
Note on AA13: Municipality of Warsaw
Note on AA15: Municipality of Warsaw
Note on AA16: Municipality of Warsaw
Note on AA17: Municipality of Warsaw
Note on AA21: Municipality of Warsaw
Note on AA22: Municipality of Warsaw